## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | Project setup, repo creation, and requirements gathering | MUST HAVE | None | Srijan Mohan Srivastava | Completed
1 | 1 | US-002 | Design system architecture and workflow diagrams | MUST HAVE | US-001 | Srijan Mohan Srivastava | Completed
2 | 2 | US-003 | Implement data collection module (news, social media APIs) | MUST HAVE | US-002 | Srijan Mohan Srivastava | Completed
2 | 2 | US-004 | Develop sentiment analysis and trend detection modules | MUST HAVE | US-003 | Srijan Mohan Srivastava | Completed
3 | 3 | US-005 | Integrate alert system for real-time notifications | SHOULD HAVE | US-004 | Srijan Mohan Srivastava | Completed
3 | 3 | US-006 | Build Flask dashboard backend and API routes | MUST HAVE | US-004 | Srijan Mohan Srivastava | Completed
4 | 4 | US-007 | Create dashboard frontend (HTML, charts, filters) | MUST HAVE | US-006 | Srijan Mohan Srivastava | Completed
4 | 4 | US-008 | Implement user filters and competitor comparison features | SHOULD HAVE | US-007 | Srijan Mohan Srivastava | Completed
4 | 4 | US-009 | Testing, bug fixing, and documentation | MUST HAVE | US-008 | Srijan Mohan Srivastava | Completed
4 | 4 | US-010 | Final deployment and project submission | MUST HAVE | US-009 | Srijan Mohan Srivastava | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 33 | 10 | 10 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Create GitHub repo and set up project structure | 2025-08-13 | 2025-08-14 | Srijan Mohan Srivastava | Setup | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-002 | Draw architecture diagram (Lucidchart) | 2025-08-15 | 2025-08-15 | Srijan Mohan Srivastava | Design | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-003 | Implement data_collector.py | 2025-08-27 | 2025-08-30 | Srijan Mohan Srivastava | Coding | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-004 | Implement sentiment_analyzer.py | 2025-09-01 | 2025-09-04 | Srijan Mohan Srivastava | Coding | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-005 | Integrate alert_system.py | 2025-09-11 | 2025-09-12 | Srijan Mohan Srivastava | Coding | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-006 | Build Flask backend and API | 2025-09-13 | 2025-09-16 | Srijan Mohan Srivastava | Coding | Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-007 | Create dashboard.html template | 2025-09-17 | 2025-09-18 | Srijan Mohan Srivastava | Frontend | Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-008 | Add filters and competitor comparison | 2025-09-19 | 2025-09-21 | Srijan Mohan Srivastava | Frontend | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-009 | Write documentation and test cases | 2025-09-20 | 2025-09-28 | Srijan Mohan Srivastava | Documentation | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-010 | Final deployment and submission | 2025-09-29 | 2025-10-05 | Srijan Mohan Srivastava | Deployment | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2 | Delay in API key approval for data sources | Used sample data for initial development
2 | 4 | Unclear requirements for competitor comparison | Discussed with mentor, clarified user story
3 | 6 | Sentiment model rate limits | Implemented retry and caching logic
4 | 8 | Chart rendering slow for large datasets | Optimized data processing and chart code
4 | 10 | Deployment issues on local server | Fixed Flask config and static file paths

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-08-13 | 2025-08-26 | Srijan Mohan Srivastava | Daily standups, early prototyping | Delaying documentation | Modular coding | Improved communication and early feedback
2 | 2 | 2025-08-27 | 2025-09-10 | Srijan Mohan Srivastava | Writing test cases early | Rushing through user stories | Code reviews | Increased test coverage and code quality
3 | 3 | 2025-09-11 | 2025-09-23 | Srijan Mohan Srivastava | Frequent deployments | Manual chart testing | Using version control | Automated deployment and chart validation scripts
4 | 4 | 2025-09-24 | 2025-10-05 | Srijan Mohan Srivastava | Final production checklist | Skipping peer review | Documenting pipeline | Ensured error handling and scalability